## Risk Register
ID | Category | Description | Consequence | Probability | Impact | Risk Level | Response
1 | Technical | Integration Failure | Loss of app functionality | Low | High | Medium | Change API / fix program code
2 | Technical | System Downtime/Latency | Lost revenue / user trust | Low | Medium | Low | Find better servers
3 | Technical | Security Vulnerabilities | Loss of user trust / development delays | Low | High | Medium | Fix vulnerabilities in code
4 | Schedule | Long Development Time | Development Delays | Medium | High | High | Make time for devlopment
5 | Schedule | Dependency Delays | Development Delays | Low | Medium | Medium | Make time for devlopment
6 | Schedule | Scope Creep | Development Delays | Low | Medium | Medium | Don't add unnecessary features
7 | Financial | High API/Data Costs | Strain the budget | Low | High | Medium | Will have to change API/Data source or adjust budget
8 | Financial | Low Return on Investment | Project will struggle to make a return | Medium | Medium | Medium | Change revenue generation method
9 | Financial | Infrastructure Costs | Strain the budget | Low | Medium | Low | Will have to adjust budget
10 | People | Lack of Domain Knowledge | Development Delays | Low | Medium | Low | Find resources to study
11 | People | Busy Life Schedule | Slowed Development | Medium | Medium | Medium | Fix life schedule
12 | People | Unplanned Development Downtime | Stopped Development | Low | High | Medium | Try to complete work ahead of time

## Communication Plan
Stakeholders | Responsibilites | Frequency | Purpose | Reporting Method
Product Owner | Project Deliverables | Weekly | Weekly Updates | Video
QA Testers | Testing and Bug Reporting | Bi-Weekly | Find issues to fix during development | Text Chat
Frontend Developer | Frontend Product Development | Bi-Weekly | Share Development Progress | Video/Text
Backend Developer | Backend Product Development | Bi-Weekly | Share Development Progress | Video/Text
UI/UX Designer | Product Visual Supervision | Bi-Weekly | Share insight on UI/UX design | Video/Text
Security Specialist | Product Security Supervision | Bi-Weekly | Share insight on security developments | Video/Text