## Roles and Responsibilities
Name | Role | Allocation | Estimated Hours | Hourly Rate | Cost
Bob | Project Manager | 15% | 90 | 40 | 3600
Jane | Frontend Developer | 30% | 180 | 40 | 7200
Jonathon | Backend Developer | 30% | 180 | 40 | 7200
Ashley | UI/UX Designer | 10% | 60 | 30 | 1800
Andrew | Tester | 10% | 60 | 30 | 1800
Kyle | Security Specialist | 5% | 30 | 30 | 900
Total |  |  | 600 |  | 22500

## Resources and Costs Plan
Item | Category | Quantity | Unit Cost | Duration (Months) | Total | Notes
Developer Labor | Labor | 600 Hours | $40/30 per hour | 3 | 22500
Cloud hosting | Infrastructure | Continuous/Monthly | $200/Month | 3 | 600 | Small size
Licenses | Tools | One-Time | 500 | N/A | 500 | Dev Tools/APIs
Contingency | Reserve | 10% | applied to total | N/A | 2360
Total |  |  |  |  | 25960

## RACI Matrix
Task/Role | Project Manager | Frontend Developer | Backend Developer | UI/UX Designer | Tester | Security Specialist
Frontend Visuals | A | R | I | C | C | I
Display Stocks and Analytics | A | R | C | C | C | I
Backend Info Handling | A | C | R | I | C | C
Ability to Purchase/Sell | A | R | C | C | C | I
Bank Integration | C | C | R | I | I | C
Backend Security | I | C | R | I | C | A
Transaction Security | I | C | R | I | C | A
Data Handling Security | I | C | R | I | C | A
Method Brainstorming | R | C | C | I | C | I
Method Implementation | A | R | R | I | C | I